## Slide 1
1 / 9

## Slide 2
KINCLAVEN PHARMACEUTICAL SERVICES
Product Development
Essentials
Assumptions · Prerequisites · The Team · The Plan
Meetings & Reporting · Problems · Completion
2 / 9

## Slide 3
ASSUMPTIONS
What must be true before development begins
1
Competent marketing managers have verified commercial desire for the product
2
Sales managers have confirmed optimal volume projections for up to five years
3
Project has a budget approved by Management
4
IP protection established or other mitigations in place
5
Active substance manufacturer(s) identified with an adequate data package (CEP, ASMF or equivalent)
6
Satisfactory technical and commercial agreements in place with the ASM
3 / 9

## Slide 4
PREREQUISITES
The foundations every successful project requires
Trained Individuals
Suitable training in each person's specific discipline — training alone does not equal competence
Experience & Competence
Demonstrated expertise beyond qualifications; desirable in all core team members
Approved Project Plan
A costed, sponsor-approved plan that defines scope, timelines, and responsibilities
Total Commitment
Individuals fully dedicated to the project — loose cannons and dead wood rarely help
Clear Communicators
People who can express ideas clearly, listen effectively, and collaborate as a team
Team Players
Collaborative mindset throughout — from project lead to specialist contributors
4 / 9

## Slide 5
THE PROJECT TEAM
Structure, selection and disciplines
Leadership
Project Lead selected by the sponsor; selects the team
For complex projects, consider a dedicated Project Manager alongside the Project Leader
Team meets regularly per plan and milestones; sub-groups are normal
Core Disciplines
Formulation
Analytics
Regulatory
Manufacturing
Quality Assurance
Procurement
Marketing
5 / 9

## Slide 6
THE PROJECT PLAN
A fundamental and critical document
01
Specific Tasks
Task responsibilities, timelines (work time and duration) and milestones clearly defined
02
Software Tools
Commercial tools such as MS Project are common but not essential
03
Dependencies
Identify dependencies — e.g. stability studies cannot begin before registration batches are complete
04
Concurrent Work
Clearly identify tasks that can proceed simultaneously to maximise efficiency
05
Task Duration
Distinguish fixed-duration tasks (e.g. batch analysis) from undefined ones (e.g. formulation development)
06
Milestone Review
Review of milestones is critical; deviations and slippage must be documented and reported
6 / 9

## Slide 7
MEETINGS, REPORTING & TRACKING PROGRESS
Culture, cadence and accountability
Culture is Critical
Open, honest and candid opinions are desired and actively encouraged throughout the project
Initiation Meeting
A comprehensive kick-off where the project leader outlines the project in detail; minuted promptly
Draft Plan Agreement
At initiation, the draft plan is discussed and agreed by all team members — may take several sittings
Scheduled Team Meetings
Meetings follow plan tasks and milestones; apologies accepted when appropriate; all discussions minuted accurately
Pre-Meeting Reporting
Progress, delays and problems reported ahead of each meeting so they can be specifically addressed
Plan Dissemination
The plan is updated after every meeting and disseminated to all team members including the sponsor
7 / 9

## Slide 8
PROBLEMS
Generally inevitable — manage them effectively
Key Principles
Problems are generally inevitable across all disciplines
Managed according to their nature — most commonly mean delay, which should be built into the plan
Rarely, problems seem irresolvable; the project leader may seek expert external advice, which may impact budget
It is relatively rare to encounter a truly irresolvable issue — but it does happen
Can you modify or adapt?
Explore reformulation, method adjustment, or process change before escalating
Has external expertise been sought?
Independent review can unlock solutions invisible to the internal team
If the plug must be pulled…
Avoid prevarication. No dead horses. Document, communicate, and move on.
8 / 9

## Slide 9
COMPLETION
Learn · Reflect · Recognise
Learn from it
Capture lessons learned formally; make them accessible to future project teams
Team Feedback
Gather honest input: how did the team function, who performed well, and why?
Issues Review
What were the primary issues that arose — and how were they resolved?
Improvements
What would you change next time? What could be done smarter?
Mistakes Made
Acknowledge errors without blame; focus on prevention for next time
Congratulate & Thank
Recognise contributions openly — completion is an achievement worth celebrating
9 / 9